## Team member
Chau Le
Dao Khau
Huy Ngo
Huy Nguyen
Khang Huynh
Phu Ta

## Chau Le
Admission System Project
Report date: 9/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Dao Khau
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Code interface for change password | Medium | 2014-07-03 | 2014-07-03 | Done |  | Chau Le
2 | Code interface for view profile | Medium | 2013-08-03 | 2014-08-03 | Done |  | Chau Le
3
4
Plan for next days
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Update header and footer |  | 2014-09-03
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1 | understand how to use ckeditor
2
3

## Dao Khau
Admission System Project
Report date: 9/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Dao Khau
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Code interface with ckeditor | High | 2014-07-03 | 2014-08-03 | Done |  | Dao Khau
2 | Integrate inteface | High | 2014-07-03 | 2014-09-03 | On-going |  | Dao Khau
3
4
Plan for next days
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Code function checkbox in interface |  | 2014-09-03
2 | Integrate inteface |  | 2014-09-03
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1 | understand how to use ckeditor
2
3

## Huy Ngo
Admission System Project
Report date: 9/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Huy Ngo
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1
2
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Huy Nguyen
Admission System Project
Report date: 10/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Huy Nguyen
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Learning TFS | High | 2014-10-03 | 2014-10-03 | On-going |  | Huy Nguyen
2 | Update testplan | High | 2014-10-03 | 2014-10-03 | On-going |  | Huy Nguyen
3 | Learning Unit Test | Medium | 2014-10-03 | 2014-10-03 | On-going |  | Huy Nguyen
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Khang Huynh
Admission System Project
Report date: 9/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Dao Khau
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Create business rule for Dictionary management on web application |  | 2014-07-03 | 2014-07-03 | Done |  | Khang Huynh
2 | Create pagination, checkbox, security code interface |  | 2014-08-03 | 2014-08-03 | Done |  | Khang Huynh
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Update dictionary-list interface |  | 2014-09-03
2 | Login with session on SpringMVC |  | 2014-09-03
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Phu Ta
Admission System Project
Report date: 9/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Phu Ta
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Coding load list-question from db | High | 2014-07-03 | 2014-07-03 | On-going |  | Phu Ta
2 | design database intranet | High | 2014-07-03 | 2014-07-03 | On-going |  | Phu Ta
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1 | design database intranet |  | 2014-09-03
2 | Coding load list-question from db |  | 2014-09-03
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1 | understand how to use ckeditor
2
3